## Resource Sheet
NutriLens — Resource Sheet
CS4044 – Fundamentals of Project Management ¦ Spring 2026 ¦ FAST-NUCES
# | Resource Name | Role | Type | Std. Rate (USD/hr) | Ovt. Rate (USD/hr) | USD→PKR | Std. Rate (PKR/hr) | Ovt. Rate (PKR/hr) | Hrs/Day | Notes
1 | Project Manager (PM) | Planning & Coordination | Work | 8 | 12 | 278 | 2224 | 3336 | 8 | Oversees schedule, risk, stakeholders
2 | ML Engineer | Machine Learning & AI | Work | 10 | 15 | 278 | 2780 | 4170 | 8 | MobileNetV2, TFLite, A* planner, Gemini
3 | Backend Developer | Flask API & Firebase | Work | 8 | 12 | 278 | 2224 | 3336 | 8 | REST API, Firestore, Gemini integration
4 | Flutter Developer | Mobile Frontend | Work | 8 | 12 | 278 | 2224 | 3336 | 8 | All Flutter screens, state management
5 | QA Engineer | Testing & Quality | Work | 5 | 8 | 278 | 1390 | 2224 | 8 | Unit, integration, UAT, performance tests
6 | UI/UX Designer | Design & Prototyping | Work | 6 | 9 | 278 | 1668 | 2502 | 8 | Wireframes, high-fi mockups, style guide
7 | DevOps Engineer | CI/CD & Deployment | Work | 7 | 10 | 278 | 1946 | 2780 | 8 | Railway/Render, GitHub CI/CD, monitoring
* USD→PKR rate: 1 USD = 278 PKR (Mar 2026 assumption). Blue = hardcoded inputs. Yellow = exchange rate cell.

## Cost Sheet
NutriLens — Time-Phased Detailed Cost Sheet
Project: Mar 1 2026 – Oct 29 2026 ¦ 8 hrs/day ¦ 10% Contingency ¦ 15% Overhead ¦ Rates in USD
Phase | Date Range | Resource | Days | Hrs/Day | Rate ($/hr) | Labor (USD) | Contingency (10%) | Overhead (15%) | Phase Total (USD)
Initiation & Planning | Mar 2 – Apr 23 | PM | 38 | 8 | 8 | 2432
|  | ML Engineer | 5 | 8 | 10 | 400
|  | Backend Developer | 3 | 8 | 8 | 192
|  | DevOps Engineer | 2 | 8 | 7 | 112
|  | Phase Subtotal |  |  |  | 3136 | 313.6 | 470.4 | 3920
Design | Mar 2 – May 11 | UI/UX Designer | 30 | 8 | 6 | 1440
|  | Backend Developer | 15 | 8 | 8 | 960
|  | ML Engineer | 8 | 8 | 10 | 640
|  | PM | 6 | 8 | 8 | 384
|  | Phase Subtotal |  |  |  | 3424 | 342.4 | 513.6 | 4280
ML Development | Apr 24 – Jun 17 | ML Engineer | 35 | 8 | 10 | 2800
|  | DevOps Engineer | 3 | 8 | 7 | 168
|  | QA Engineer | 5 | 8 | 5 | 200
|  | Phase Subtotal |  |  |  | 3168 | 316.8 | 475.2 | 3960
Backend Development | May 12 – Aug 21 | Backend Developer | 68 | 8 | 8 | 4352
|  | ML Engineer | 10 | 8 | 10 | 800
|  | QA Engineer | 15 | 8 | 5 | 600
|  | DevOps Engineer | 8 | 8 | 7 | 448
|  | PM | 5 | 8 | 8 | 320
|  | Phase Subtotal |  |  |  | 6520 | 652 | 978 | 8150
Frontend Flutter Dev | Jun 18 – Jul 28 | Flutter Developer | 27 | 8 | 8 | 1728
|  | UI/UX Designer | 8 | 8 | 6 | 384
|  | QA Engineer | 5 | 8 | 5 | 200
|  | Backend Developer | 5 | 8 | 8 | 320
|  | Phase Subtotal |  |  |  | 2632 | 263.2 | 394.8 | 3290
Testing & QA | Aug 24 – Oct 2 | QA Engineer | 29 | 8 | 5 | 1160
|  | Flutter Developer | 10 | 8 | 8 | 640
|  | ML Engineer | 5 | 8 | 10 | 400
|  | Backend Developer | 5 | 8 | 8 | 320
|  | DevOps Engineer | 3 | 8 | 7 | 168
|  | PM | 5 | 8 | 8 | 320
|  | Phase Subtotal |  |  |  | 3008 | 300.8 | 451.2 | 3760
Deployment | Jul 29 – Aug 18 | DevOps Engineer | 14 | 8 | 7 | 784
|  | Flutter Developer | 5 | 8 | 8 | 320
|  | Backend Developer | 5 | 8 | 8 | 320
|  | PM | 5 | 8 | 8 | 320
|  | QA Engineer | 3 | 8 | 5 | 120
|  | Phase Subtotal |  |  |  | 1864 | 186.4 | 279.6 | 2330
Project Closure | Oct 5 – Oct 29 | PM | 19 | 8 | 8 | 1216
|  | DevOps Engineer | 5 | 8 | 7 | 280
|  | Flutter Developer | 3 | 8 | 8 | 192
|  | Phase Subtotal |  |  |  | 1688 | 168.8 | 253.2 | 2110
GRAND TOTAL | [5 empty] | 25440 | 2544 | 3816 | 31800
GRAND TOTAL (PKR 1 USD = 278) | [5 empty] | 7072320 | 707232 | 1060848 | 8840400

## Summary
NutriLens — Project Budget Summary
CS4044 – Fundamentals of Project Management ¦ Spring 2026
1 | Project Name | NutriLens – AI-Powered Food & Macro Tracker
2 | Organization | FAST-NUCES Karachi
3 | Course | CS4044 – Fundamentals of Project Management
4 | Start Date | 2nd March 2026
5 | End Date | 29th October 2026
6 | Duration | ~8 Months
7 | Team Size | 7 Resources
8 | Contingency | 10% per phase
9 | Overhead | 15% per phase (cloud, APIs, licenses)
10 | Exchange Rate | 1 USD = 278 PKR
# | Phase | Date Range | Days | Labor (USD) | Phase Total (USD) | Phase Total (PKR)
1 | Initiation & Planning | Mar 2 – Apr 23 | 38 | 3136 | 3920 | 1089760
2 | Design | Mar 2 – May 11 | 49 | 3424 | 4280 | 1189840
3 | ML Development | Apr 24 – Jun 17 | 35 | 3168 | 3960 | 1100880
4 | Backend Development | May 12 – Aug 21 | 68 | 6520 | 8150 | 2265700
5 | Frontend Flutter Dev | Jun 18 – Jul 28 | 27 | 2632 | 3290 | 914620
6 | Testing & QA | Aug 24 – Oct 2 | 29 | 3008 | 3760 | 1045280
7 | Deployment | Jul 29 – Aug 18 | 14 | 1864 | 2330 | 647740
8 | Project Closure | Oct 5 – Oct 29 | 19 | 1688 | 2110 | 586580
GRAND TOTAL |  |  |  | 25440 | 31800 | 8840400
Key Budget Metrics
Total Labor Cost (USD) |  |  |  | 25440
Total Contingency (USD) |  |  |  | 2544
Total Overhead (USD) |  |  |  | 3816
Grand Total Budget (USD) |  |  |  | 31800
Grand Total Budget (PKR) |  |  |  | 8840400
Contingency as % of Labor |  |  |  | 10%
Overhead as % of Labor |  |  |  | 15%
Avg. Daily Cost (USD) |  |  |  | 133.0544
* Overhead covers: Railway/Render hosting, Google Gemini API, Firebase Blaze plan, GitHub Pro, Figma, testing devices, and miscellaneous tools.