FAST-NUCES KARACHI CAMPUS

(SPRING-2026)

(CS-4044) SOFTWARE PROJECT MANAGEMENT

[NUTRI-LENS: AI-POWERED FOOD & MACRO TRACKER MOBILE APP]

SECTION:

BS-CS-6A

INSTRUCTOR:

SIR UBAID AFTAB

MEMBERS:

K230830 HASSAN SHAIKH

P230560 ABDUL RAFY

K230907 ZUBAIR AHMED

YOUSUF

# 1. BUSINESS STATEMENT

## 1.1. ORGANIZATION BACKGROUND (THE VENDOR)

NutriLens is being developed by HealthTech AI Solutions, a small software development team specializing in artificial intelligence applications for personal wellness and nutrition. The team combines expertise in machine learning (MobileNetV2, TensorFlow), mobile development (Flutter), and cloud backend services (Firebase, Python/Flask).

HealthTech AI Solutions has previously delivered two successful health-tracking prototypes and focuses on solving real user frustrations through intelligent automation. The team’s core philosophy is to eliminate manual data entry by leveraging on-device and cloud AI.

## 1.2. OPPORTUNITY OR PROBLEM THAT THE PROJECT WILL ADDRESS (THE CLIENT NEED)

[THE PROBLEM]

Existing calorie-tracking apps (e.g., MyFitnessPal) suffer from three major issues:

- Manual logging is tedious: users must search databases, weigh portions, and enter every item. This leads to high abandonment rates.

- Poor accuracy for local cuisines: standard databases lack South Asian dishes (biryani, karahi, halwa puri, paratha), making tracking unreliable for a large user base.

- No intelligent guidance: users only see past totals; they receive no proactive recommendations on what to eat next to meet their daily macro goals.

[THE OPPORTUNITY]

NutriLens fills this gap by providing a seamless, AI-powered alternative:

- Snap-to-log: users photograph a meal; the app classifies it and estimates macros.

- South-Asian-aware: future custom dataset will address local cuisine; initially, top-3 classification with confidence scores manages accuracy.

- Intelligent meal planning: an A* search algorithm recommends remaining meals to help users hit their daily protein, calorie, and fat targets.

By reducing logging time from minutes to seconds and offering actionable recommendations, NutriLens will increase user retention and provide a competitive advantage in the wellness app market.

# 2. PROJECT TEAM

## 2.1. REQUIRED RESOURCES

| RESOURCE TYPE | QTY | KEY RESPONSIBILITIES | JUSTIFICATION |
| --- | --- | --- | --- |
| Project Manager (PM) | 1 | Overall planning, budget tracking, risk management, client communication, sprint coordination. | Ensures the project stays on schedule (6:9 months) and within budget; acts as the primary link between the team and stakeholders. |
| ML Engineer | 1 | Data preparation (Food‑101 dataset), training MobileNetV2 model, model evaluation, conversion to TensorFlow Lite, integration with Gemini API. | Core AI functionality (food classification, portion estimation) requires dedicated ML expertise. |
| Backend Developer | 1 | Build Flask REST API, integrate Gemini Flash 2.0, implement A* meal planner, manage Firebase Firestore, deploy on Railway/Render. | Handles all server‑side logic, database operations, and API security. |
| Flutter Developer | 1 | Develop all UI screens (onboarding, camera, dashboard, history, streak, profile), state management (Provider), Firebase Auth integration, camera plugin. | Delivers the cross‑platform mobile experience (Android first, iOS later). |
| QA / Tester | 1 | Write test cases, perform unit/integration testing, UI testing, load testing (API), manage bug tracking. | Ensures app stability, classification accuracy, and performance before release. |
| UI/UX Designer | 1 | Design wireframes, high‑fidelity mockups, user flows, and visual assets; conduct usability tests. | A clean, intuitive interface is critical for user adoption (non‑technical users). |
| DevOps Engineer (part‑time) | 0.5 | Set up CI/CD pipeline, manage cloud deployments, monitor API uptime, configure Firebase security rules. | Automates releases and ensures production reliability; shared across projects. |
| Nutrition Expert (Consultant) | 1 (external) | Validate macro calculations, meal database nutritional values, and dietary filters. | Ensures the app’s nutrition logic is |

TOTAL TEAM SIZE: 7 full-time equivalent (6 full-time + 1 part-time + external consultant)

## 2.2. PROJECT TEAM STRUCTURE

The team will follow an AGILE SCRUM structure with two-week sprints:

- Product Owner (Pm Role): Manages the backlog, prioritizes features (e.g., classification accuracy first, then A* planner).

- Scrum Master (Pm Role): Facilitates daily stand-ups, removes impediments.

- Development sub-teams:

  - ML & Backend (ML Engineer + Backend Developer): work closely on API endpoints and model serving.

  - Frontend (Flutter Developer + UI/UX Designer): deliver UI components and integrate with APIs.

  - QA works across both sub-teams.

  - DevOps supports deployment at the end of each sprint.

REASONING: This structure enables parallel work (ML training while frontend is built), ensures continuous integration (CI/CD), and provides clear ownership. The external nutrition expert reviews deliverables incrementally to avoid last-minute corrections.

# 3. FEASIBILITY ANALYSIS

## 3.1. FOUR TYPES OF FEASIBILITY (RATED 1:10)

| FEASIBILITY TYPE | RATING (1-10) | JUSTIFICATION |
| --- | --- | --- |
| Technical Feasibility | 9/10 | The technology stack is mature and well‑documented: MobileNetV2 (pre‑trained on Food‑101), TensorFlow Lite for on‑device inference, Flask for API, Firebase for backend, Flutter for cross‑platform UI. The team has prior experience with each component. The only technical risk is achieving <2s inference on average Android devices: mitigated by model quantization and optional cloud fallback. |
| Operational Feasibility | 8/10 | The app directly solves a real user pain point (manual logging). The user flow (snap → classify → log → plan) is intuitive and requires minimal training. However, user adoption depends on classification accuracy (especially for mixed dishes). Mitigation: show top‑3 candidates with confidence scores and allow manual correction. The South Asian cuisine gap is noted but not a blocker for MVP. |
| Economic Feasibility | 7/10 | Initial development cost (6:9 months for a team of 6:7) is moderate. Ongoing costs: Firebase (free tier up to 50K reads/day), Gemini API (pay‑as‑you‑go), and cloud hosting (Railway free tier initially). Monetization (freemium or subscription) is planned post‑launch. ROI is positive if the app achieves 10,000+ active users within 6 months of launch. A detailed budget will confirm viability. |
| Schedule Feasibility | 8/10 | The 6:9 month timeline is realistic: 2 months for planning/design, 2 months for ML training, 2:3 months for backend + frontend parallel development, 1 month for testing and deployment. The risk of delays in model training is mitigated by using a pre‑trained MobileNetV2 (transfer learning). Adding a second developer (Flutter + backend) allows parallel work. |

## 3.2. CRITICAL SUCCESS FACTORS (CSFS)

| CSF | Why Critical | Measures Taken |
| --- | --- | --- |
| High classification accuracy (≥75% Top‑1) | Users will abandon the app if food is frequently misidentified. | Use Food‑101 (101k images); fine‑tune MobileNetV2; show top‑3 results; allow manual override. |
| Low latency (<2 seconds from snap to log) | Slow processing frustrates users and breaks the seamless experience. | Optimize model size (TensorFlow Lite); run inference on‑device; use caching for repeated meals. |
| Accurate macro estimation | Incorrect calorie counts destroy trust and make meal planning useless. | Use Gemini Flash 2.0 for portion estimation; nutrition expert validates meal database; unit tests for TDEE calculations. |
| User retention (weekly streak) | The app must keep users engaged beyond the first week. | Implement streak tracking, push reminders, and personalized meal recommendations. |
| Successful launch on Google Play Store | Without distribution, the app cannot reach users. | Pre‑launch testing with 50 beta users; comply with Play Store policies; prepare marketing assets. |

# 4. PROJECT GOAL / PURPOSE / AIM / OBJECTIVES

## 4.1. AIM OF THE PROJECT

The primary aim of NutriLens is to develop and launch an AI-powered mobile application that eliminates manual food logging by enabling users to photograph their meals, automatically receive macro estimates, and get intelligent recommendations for remaining meals to achieve daily nutrition goals.

## 4.2. SMART GOALS (WHAT THE PROJECT WILL MEET)

| GOAL | SMART STATEMENT |
| --- | --- |
| 1. Classification Accuracy | Achieve ≥75% Top‑1 accuracy and ≥90% Top‑5 accuracy on the Food‑101 test set for the MVP release. (Measured via model evaluation on a held‑out test set.) |
| 2. Response Time | Maintain average end‑to‑end latency of <2 seconds from photo capture to macro log display on a mid‑range Android device (e.g., Samsung A series). (Measured via performance testing on 5 device models.) |
| 3. User Onboarding Completion | Achieve ≥85% onboarding completion rate (users finish all 5 setup steps). (Measured via Firebase Analytics funnel tracking.) |
| 4. First‑Week Retention | Retain ≥40% of new users for at least 7 days after first log (i.e., they log at least one more meal in the second week). (Measured via streak and daily active users.) |
| 5. Meal Plan Usefulness | Achieve ≥4.0/5.0 average user rating for the AI meal planner feature in a post‑MVP survey. (Measured via in‑app feedback form.) |

## 4.3. BENEFITS TO THE ORGANISATION (HEALTHTECH AI SOLUTIONS)

| BENEFIT | EXPLANATION |
| --- | --- |
| Market Differentiation | NutriLens provides the first South‑Asian‑aware, snap‑to‑log tracker with proactive meal planning: a unique value proposition compared to MyFitnessPal and Lose It!. |
| Recurring Revenue Potential | A freemium model (free for basic logging, subscription for AI meal planner and advanced analytics) creates a sustainable revenue stream. |
| Portfolio Expansion | Successfully launching an AI‑powered health app demonstrates the team’s capability in computer vision, LLM integration (Gemini), and mobile development: attracting future clients or investors. |
| User Data & Insights | Aggregated, anonymized meal data can be used to improve the model and identify dietary trends, opening opportunities for partnerships with nutrition brands or research institutions. |

# 5. PROJECT DELIVERABLES

## 5.1. LIST OF DELIVERABLES

| DELIVERABLE ID | DELIVERABLE NAME | DESCRIPTION |
| --- | --- | --- |
| D1 | Trained MobileNetV2 Model | A TensorFlow Lite model fine‑tuned on Food‑101 dataset, capable of classifying 101 food categories with ≥75% Top‑1 accuracy. |
| D2 | Flask REST API Backend | Python/Flask API with endpoints for food classification, portion estimation (Gemini integration), A* meal planning, and macro calculations. |
| D3 | Firebase Firestore Database | Cloud database schema for users, meal logs, meal database (200‑300 meals), and streak data. |
| D4 | Flutter Mobile Application | Cross‑platform app (Android first) with all screens: onboarding, camera, macro dashboard, history, meal planner, profile, streak tracker. |
| D5 | User Authentication Module | Firebase Auth integration supporting Email/Password and Google Sign‑In. |
| D6 | AI Meal Planner (A* Algorithm) | Backend module that recommends remaining meals to close macro gaps, re‑running after each logged meal. |
| D7 | Portion Estimation Module | Integration with Google Gemini Flash 2.0 to estimate portion size and refine macros from a meal photo. |
| D8 | Weekly Streak Tracker | UI component and backend logic tracking consecutive days of logging at least one meal, with visual 7‑day view. |
| D9 | Onboarding Flow (5 Steps) | Complete user setup capturing name, gender, age, weight, height, fitness goal, dietary preference. |
| D10 | Macro Dashboard | Real‑time display of daily calories, protein, carbs, fat vs. user’s personalized targets (calculated via Mifflin‑St Jeor). |
| D11 | Meal Log History | Paginated history of all logged meals with timestamps, images, and macro breakdowns. |
| D12 | Dietary Filters | UI toggle to filter meal recommendations by Vegetarian, Non‑Veg, or Both. |
| D13 | User Acceptance Testing (UAT) Report | Documented feedback from 20 beta users, including bug reports and satisfaction ratings. |
| D14 | Deployment Package | Production build of backend (Railway/Render) and mobile app (Google Play Store internal track). |
| D15 | Technical & User Documentation | API documentation (Swagger), user manual, and maintenance guide for future developers. |

## 5.2. LINKING OBJECTIVES TO DELIVERABLES

Each SMART goal from Section 4 is supported by specific deliverables:

| SMART GOAL (FROM SECTION 4.2) | SUPPORTING DELIVERABLE(S) |
| --- | --- |
| Goal 1: ≥75% Top‑1 accuracy | D1 (Trained MobileNetV2 Model): evaluation on test set |
| Goal 2: <2 sec end‑to‑end latency | D2 (Flask API optimized), D4 (Flutter app with efficient camera), D7 (Gemini call with timeout) |
| Goal 3: ≥85% onboarding completion | D9 (Onboarding Flow): analytics events to track drop‑offs |
| Goal 4: ≥40% first‑week retention | D8 (Streak Tracker), D10 (Macro Dashboard), D6 (AI Meal Planner): features that encourage return |
| Goal 5: ≥4.0/5.0 rating for meal planner | D6 (A* Meal Planner): user feedback collected via in‑app survey |

## 5.3. SUCCESS CRITERIA (ACCEPTANCE CRITERIA FOR DELIVERABLES)

| DELIVERABLE | SUCCESS CRITERIA (HOW WE KNOW IT’S DONE) |
| --- | --- |
| D1: Trained MobileNetV2 Model | Model evaluation on held‑out Food‑101 test set shows Top‑1 accuracy ≥75% and Top‑5 ≥90%. Model size <50 MB for on‑device inference. |
| D2: Flask REST API | All endpoints respond with <500ms latency under load testing (50 concurrent users). Swagger documentation is complete. |
| D3: Firestore Database | All collections are indexed; security rules prevent unauthorised access; backup schedule defined. |
| D4: Flutter Mobile App | App builds without errors for Android; all screens render correctly on devices with screen sizes from 5" to 6.5". No crashes during 2 hours of continuous use. |
| D5: Authentication | Users can sign up with email/password and Google; session persists across app restarts; logout works. |
| D6: AI Meal Planner | Given current macros and target, the planner returns 3 meal suggestions within 1 second. Suggestions respect dietary filters. |
| D7: Portion Estimation | Gemini API returns portion size (small/medium/large) and macro adjustment within 3 seconds; graceful fallback if API fails (uses average portion). |
| D8: Weekly Streak Tracker | Streak increments correctly when user logs at least one meal per calendar day; streak resets after a missed day; UI shows last 7 days with highlights. |
| D9: Onboarding Flow | 100% of users who start onboarding can complete all 5 steps; each step has validation (e.g., age 13‑100, weight >0). |
| D10: Macro Dashboard | Dashboard updates in real time after each meal log; progress bars show % of daily goal; TDEE calculation matches Mifflin‑St Jeor formula. |
| D11: Meal Log History | History shows reverse chronological list with thumbnail, food name, macros, and timestamp. Pagination loads 20 items at a time. |
| D12: Dietary Filters | Toggle between Vegetarian, Non‑Veg, Both instantly refreshes recommended meals; meal database includes dietary tag for each meal. |
| D13: UAT Report | At least 20 beta users complete 7 days of testing; zero critical bugs (P1) remain; average satisfaction ≥4.0/5.0. |
| D14: Deployment Package | Backend deployed on Railway/Render with environment variables; Android app published to Play Store internal testing track. |
| D15: Documentation | API endpoints documented with Swagger UI; user manual includes screenshots and FAQs; maintenance guide explains database backup and model update process. |

# 6. PROJECT SCOPE

## 6.1. PRODUCT SCOPE (FEATURES AND CHARACTERISTICS)

NutriLens is an AI-powered mobile application that enables users to track food intake and receive intelligent meal recommendations. The high-level features are:

- Snap-to-Log Photography: Users capture a meal photo; the app classifies the food and estimates macros.

- Real-Time Macro Dashboard: Daily progress toward personalized calorie, protein, carbs, and fat targets.

- AI Meal Planner (A Algorithm): Recommends remaining meals to help users meet their daily goals.

- User Onboarding (5 Steps): Collects body stats, fitness goal, and dietary preference to calculate TDEE and macro targets.

- Authentication: Email/Password and Google Sign-In via Firebase Auth.

- Meal Log History: Paginated list of past meals with images and macro details.

- Weekly Streak Tracker: Visual 7-day streak to encourage consistent logging.

- Dietary Filters: Meal recommendations filterable by Vegetarian, Non-Veg, or Both.

- Profile Management: Users can update body stats, goal, and dietary preference.

## 6.2. PROJECT BOUNDARIES: INCLUSIONS AND EXCLUSIONS

### 6.2.1. INCLUSIONS (WHAT IS IN SCOPE)

| AREA | DETAILS |
| --- | --- |
| Mobile Application | Flutter‑based app for Android (primary). Codebase supports iOS but full iOS testing is out of scope for MVP. |
| Food Classification | MobileNetV2 model trained on Food‑101 dataset (101 categories). Model runs on‑device (TensorFlow Lite). |
| Portion Estimation | Integration with Google Gemini Flash 2.0 API to estimate portion size and adjust macros. |
| Meal Planner | A* search algorithm using a curated meal database (200:300 meals). Runs on backend (Flask). |
| Backend API | Flask REST API deployed on Railway/Render, handling classification, Gemini calls, and meal planning. |
| Database | Firebase Firestore for user profiles, meal logs, meal database, streak data. |
| Authentication | Firebase Auth (Email/Password, Google Sign‑In). |
| User Onboarding | 5‑step setup: name, gender, age, weight, height, fitness goal, dietary preference. |
| Macro Calculation | Mifflin‑St Jeor BMR formula + activity factor to set daily calorie and macro targets. |
| Streak Tracking | Consecutive days with at least one logged meal. Resets after a missed day. |
| History & Filters | Paginated meal log history; dietary filters applied to meal planner. |
| Documentation | API Swagger docs, user manual, maintenance guide. |
| Deployment | Production backend on Railway/Render; Android app on Google Play Store internal track. |

### 6.2.2. EXCLUSIONS (WHAT IS OUT OF SCOPE)

| AREA | REASON |
| --- | --- |
| iOS App Store Release | MVP focuses on Android; iOS will be a future update after validation. |
| Custom South Asian Food Dataset | Food‑101 lacks many desi dishes; custom dataset is post‑MVP work. |
| Wearable Integration | No smartwatch or fitness band connectivity. |
| Barcode / QR Scanning | Not included; only photo‑based logging. |
| Social Features | No sharing, following, or community feeds. |
| In‑App Nutritionist Consultations | No direct messaging or booking with dietitians. |
| Multi‑Language Support | English only for MVP. |
| Offline Mode | Requires internet for API calls (classification, Gemini, meal planner). |
| Advanced Analytics | No export of data to CSV/PDF; only in‑app dashboard. |
| Payment / Subscription | MVP is free; monetization is future scope. |

## 6.3. PROJECT PHASES AND MILESTONES

| PHASE | DURATION | GOAL | KEY ACTIVITIES | DELIVERABLE(S) |
| --- | --- | --- | --- | --- |
| Phase 1: Planning & Analysis | Month 1 (Mar 2026) | Define scope, team, feasibility | Requirements gathering, risk assessment, expert consultation, finalize WBS | Signed project plan, WBS |
| Phase 2: Design | Month 2 (Apr 2026) | Architecture, UI/UX, database design | Wireframes, database schema, API design, model architecture | UI mockups, ERD, API spec |
| Phase 3: ML Development | Months 3:4 (May:Jun 2026) | Train and evaluate MobileNetV2 | Data prep, transfer learning, model tuning, TensorFlow Lite conversion | Trained model (D1) |
| Phase 4: Backend Development | Months 3:5 (May:Jul 2026) | Build API, Gemini integration, A* planner | Flask endpoints, Firestore integration, meal database population | Flask API (D2), Meal planner (D6) |
| Phase 5: Frontend Development | Months 4:6 (Jun:Aug 2026) | Build Flutter app, all screens | Onboarding, camera, dashboard, history, streak, profile | Flutter app (D4), Auth (D5) |
| Phase 6: Testing & QA | Months 6:7 (Aug:Sep 2026) | System testing, UAT, bug fixes | Unit/integration tests, load tests, beta testing (20 users) | UAT report (D13) |
| Phase 7: Deployment & Closure | Month 7:8 (Sep:Oct 2026) | Production release, documentation, handover | Deploy backend, publish Android app, create docs | Deployment (D14), Documentation (D15) |

Total estimated duration: 7:8 months (well within the 6-12 month requirement).

## 6.4. SUCCESS CRITERIA FOR THE PROJECT

The project is considered successful when all the following are met:

| CRITERION | TARGET | MEASUREMENT METHOD |
| --- | --- | --- |
| Classification accuracy | ≥75% Top‑1, ≥90% Top‑5 | Model evaluation on test set |
| End‑to‑end latency | <2 seconds (photo to log) | Performance testing on 5 Android devices |
| Onboarding completion | ≥85% of users finish all 5 steps | Firebase Analytics funnel |
| First‑week retention | ≥40% of new users log again in week 2 | Streak and DAU metrics |
| Meal planner rating | ≥4.0/5.0 from UAT users | In‑app survey after 5 uses |
| Zero critical bugs | No P1 (crash/data loss) bugs at launch | UAT and QA sign‑off |
| Play Store approval | App accepted in internal testing track | Google Play Console |
| Documentation completion | API docs, user manual, maintenance guide reviewed | Stakeholder sign‑off |

## 6.5. SOFTWARE PROCESS MODEL

### 6.5.1. Model Selected: AGILE SCRUM

[RATIONALE FOR NUTRILENS]

| PROJECT CHARACTERISTIC | HOW SCRUM ADDRESSES IT |
| --- | --- |
| AI/ML uncertainty | Model accuracy may require multiple iterations; Scrum’s sprints allow retraining and re‑evaluation every 2 weeks. |
| Cross‑functional team | ML, backend, frontend, QA work in parallel; Scrum’s daily stand‑ups and sprint planning ensure alignment. |
| User feedback dependency | Beta testing (UAT) feedback is incorporated into subsequent sprints: essential for refining UI and meal planner. |
| Changing requirements | Dietary filters or new fitness goals may be added; Product Owner prioritizes backlog without disrupting core schedule. |
| Fast time‑to‑market | Scrum delivers a shippable increment each sprint; MVP can be released after Sprint 6 (core features), with enhancements later. |

### 6.5.2. SCRUM IMPLEMENTATION DETAILS:

- Sprint length: 2 weeks

Roles:

  - Product Owner: Project Manager (manages backlog)

  - Scrum Master: Project Manager (facilitates ceremonies)

  - Development Team: ML Engineer, Backend Dev, Flutter Dev, QA, UI/UX Designer (part-time)

- Ceremonies: Sprint Planning (2 hours), Daily Stand-up (15 min), Sprint Review (1 hour), Sprint Retrospective (1 hour)

- Artifacts: Product Backlog (features + technical tasks), Sprint Backlog, Burndown Chart

Why Not Waterfall?
ML model performance cannot be fully predicted upfront; Waterfall would risk discovering low accuracy late in the cycle. Scrum’s iterative nature allows early validation of the classification model (Sprint 2:3) before full frontend integration.

# 7. AGILE USER STORIES

## 7.1. NEW USER (GUEST) STORIES

| # | USER STORY |
| --- | --- |
| US‑01 | As a new user, I want to download the app from the Google Play Store so that I can install it on my Android device. |
| US‑02 | As a new user, I want to complete a 5‑step onboarding process (name, gender, age, weight, height, goal, diet preference) so that the app can calculate my personalized daily macro targets. |
| US‑03 | As a new user, I want to see my calculated daily calorie and macro targets at the end of onboarding so that I understand what I am working toward. |
| US‑04 | As a new user, I want to create an account using email/password or Google Sign‑In so that my meal logs and streak are saved across sessions. |
| US‑05 | As a new user, I want to skip account creation temporarily and use a guest mode so that I can test the app before committing to registration. |

## 7.2. REGISTERED USER (PRIMARY USER) STORIES

| # | USER STORY |
| --- | --- |
| US‑06 | As a registered user, I want to log in with my email or Google account so that I can access my personal dashboard and history. |
| US‑07 | As a registered user, I want to open the camera from the home screen and photograph my meal so that the app automatically identifies the food and estimates its macros without manual entry. |
| US‑08 | As a registered user, I want to see the top 3 food classification results with confidence scores so that I can confirm or correct the identification if needed. |
| US‑09 | As a registered user, I want the app to estimate portion size (small/medium/large) using AI so that I don’t have to guess or weigh my food. |
| US‑10 | As a registered user, I want to view a real‑time macro dashboard showing my remaining calories, protein, carbs, and fat for the day so that I know how I am progressing toward my goal. |
| US‑11 | As a registered user, I want the app to automatically recommend 2‑3 meals for the rest of the day based on my remaining macros so that I don’t have to plan manually. |
| US‑12 | As a registered user, I want to filter meal recommendations by Vegetarian, Non‑Veg, or Both so that the suggestions match my dietary preferences. |
| US‑13 | As a registered user, I want to view a paginated history of all my logged meals with timestamps and macro breakdowns so that I can track my eating patterns over time. |
| US‑14 | As a registered user, I want to see a 7‑day streak indicator that highlights which days I logged meals so that I stay motivated to log consistently. |
| US‑15 | As a registered user, I want to edit or delete a logged meal in case I made a mistake or the AI misclassified it. |
| US‑16 | As a registered user, I want to update my profile (weight, goal, dietary preference) so that my macro targets adjust when my fitness journey changes. |
| US‑17 | As a registered user, I want to receive a push notification at my chosen dinner time reminding me to log my meal so that I don’t forget to maintain my streak. |
| US‑18 | As a registered user, I want to rate the AI meal planner (1‑5 stars) after using it so that the development team can improve recommendations. |

## 7.3. ADMIN / BACKEND OPERATOR STORIES

| # | USER STORY |
| --- | --- |
| US‑19 | As an admin, I want to log into a secure web dashboard so that I can manage the meal database (add, edit, or remove meals and their macro values). |
| US‑20 | As an admin, I want to upload a new version of the MobileNetV2 model (retrained) without taking the backend offline so that classification accuracy can improve over time. |
| US‑21 | As an admin, I want to monitor API health (uptime, latency, error rates) via a simple status page so that I can detect and fix issues before users are affected. |
| US‑22 | As an admin, I want to view anonymous usage analytics (e.g., most frequently logged foods, average session length) so that I can prioritize future features (e.g., custom South Asian dataset). |

# 8. Assumptions, Constraints and Dependencies

## 8.1. Assumptions Made

| # | ASSUMPTION | WHY IT MATTERS |
| --- | --- | --- |
| A1 | The Food‑101 dataset (101,000 images, 101 categories) is sufficient for MVP classification accuracy (≥75% Top‑1). | If accuracy falls below threshold, additional training data or a different model would be required, impacting schedule. |
| A2 | Target users own an Android device with a functional camera and internet connection. | The app requires both hardware (camera) and network (API calls) to function. Offline mode is out of scope. |
| A3 | Users will complete the 5‑step onboarding process without significant drop‑off. | Onboarding completion rate of ≥85% is a success criterion; if lower, UX redesign would be needed. |
| A4 | Google Gemini Flash 2.0 API remains available at current pricing (or free tier) throughout development. | Any major pricing change or API deprecation would increase costs or require an alternative solution. |
| A5 | The curated meal database (200:300 meals) with accurate macro values can be prepared by the backend developer and nutrition expert within 1 month. | Without a quality meal database, the A* planner cannot provide useful recommendations. |
| A6 | Beta testers (20 users) will be available for UAT during Months 6:7. | User acceptance testing is critical for identifying bugs and measuring satisfaction. |
| A7 | The development team (7 members) remains available full‑time for the 7:8 month duration. | Any loss of key personnel (e.g., ML Engineer) would delay the project. |

## 8.2. Constraints

### 8.2.1. Time Constraints

| CONSTRAINT | DETAILS |
| --- | --- |
| Fixed launch window | The app must be ready for beta testing by end of Month 6 (August 2026) and production release by end of Month 8 (October 2026) to align with university semester schedule (if targeted at students). |
| No extension for ML training | Model training and tuning cannot exceed 2 months (Months 3:4) without delaying backend and frontend integration. |

### 8.2.2. Resource Constraints

| CONSTRAINT | DETAILS | CONSTRAINT |
| --- | --- | --- |
| Team size limited to 7 full‑time equivalents | No additional developers or budget for outsourcing. Work must be distributed across existing roles. | Team size limited to 7 full‑time equivalents |
| One ML Engineer | If the ML Engineer is unavailable, model development stops. Cross‑training is limited. | One ML Engineer |
| Part‑time DevOps (0.5 FTE) | Deployment pipeline and monitoring may have slower turnaround times. | Part‑time DevOps (0.5 FTE) |

### 8.2.3. Financial Constraints

| CONSTRAINT | DETAILS |
| --- | --- |
| Fixed budget (to be defined in Section 13) | Cloud costs (Firebase, Gemini API, Railway hosting) must stay within free tier or minimal usage limits for MVP. |
| No paid marketing budget | User acquisition relies on organic growth, word of mouth, and possibly university partnerships. |

### 8.2.4. Business Constraints

| CONSTRAINT | DETAILS |
| --- | --- |
| No revenue generation in MVP | The app will be completely free; monetization (subscription, ads) is future scope. |
| Must comply with Google Play Store policies | Privacy policy, data handling, and age restrictions must be clearly documented. |

### 8.2.5. Technical Constraints

| CONSTRAINT | DETAILS |
| --- | --- |
| On‑device model size <50 MB | MobileNetV2 must be quantized to meet this limit; larger models would increase app size and reduce download conversion. |
| API response time <500ms (excluding Gemini) | Backend must be optimized; using free tier hosting (Railway) may introduce cold starts. |
| No offline functionality | All core features (classification, portion estimation, meal planning) require internet. |
| Android minimum version API 24 (Android 7.0) | Ensures compatibility with 90%+ of active Android devices. |

## 8.3. Dependencies (External Factors)

| # | DEPENDENCY | IMPACT IF DELAYED | MITIGATION STRATEGY |
| --- | --- | --- | --- |
| D1 | Google Gemini Flash 2.0 API availability | Portion estimation module cannot be built or tested. | Have a fallback: use average portion sizes (small/medium/large) with user confirmation. |
| D2 | Firebase project setup & authentication | User accounts and database cannot be created. | PM requests Firebase project creation from team lead during Week 1 of Phase 1. |
| D3 | Food‑101 dataset download & licensing | Model training cannot start. | Download dataset during Phase 2 (Design) so it is ready for Phase 3. Ensure dataset is freely usable for research/commercial purposes. |
| D4 | Availability of nutrition expert for meal database validation | Meal database may contain incorrect macro values, breaking the A* planner’s accuracy. | Recruit expert during Phase 1; have backend developer prepare initial draft for expert review in Month 2. |
| D5 | Beta tester recruitment (20 users) | UAT cannot be completed, leaving critical bugs undiscovered. | PM recruits beta testers from university student groups during Month 5 (before testing phase). Offer incentives (e.g., free premium future access). |
| D6 | Google Play Store developer account approval | App cannot be published on Play Store (even internal track). | PM registers and pays one‑time fee ($25) during Phase 1; ensures account is approved by Month 2. |
| D7 | Railway/Render free tier limitations | API may experience cold starts or rate limiting, affecting user experience. | Monitor usage; if necessary, upgrade to paid tier (minimal cost, $5:20/month) during beta testing. |

# 9. Stakeholders

## 9.1. Identification and Roles of Various Stakeholders

Stakeholders in the NutriLens project include both internal (development team) and external (client, users, experts) parties who have an interest in the project’s success or are affected by its outcome.

### 9.1.1. External Stakeholders:

- End Users (Students / General Public): Individuals who will download and use the NutriLens app to track meals and receive recommendations. Their primary role is to provide feedback during beta testing and adopt the app post-launch.

- Beta Testers (20 selected users): A subset of end users who participate in User Acceptance Testing (UAT) during Months 6:7. They are responsible for logging meals, reporting bugs, and completing satisfaction surveys.

- Nutrition Expert (Consultant): An external specialist (e.g., certified dietitian or nutrition professor) who validates the macro values of the meal database and reviews the Mifflin-St Jeor calculations. Their role is to ensure scientific accuracy and credibility.

- Google / Firebase Platform Providers: Not active stakeholders but dependencies. Their terms of service and API availability affect the project. No direct role in decision-making.

### 9.1.2. Internal Stakeholders (HealthTech AI Solutions Team):

- Project Manager (PM): Owns the overall plan, budget, risk register, and stakeholder communication. Acts as the primary liaison between the development team and external parties.

- ML Engineer: Responsible for delivering the trained MobileNetV2 model (Deliverable D1) and ensuring classification accuracy meets the success criterion (≥75% Top-1). The ML Engineer also advises on model update procedures.

- Backend Developer: Builds the Flask API, integrates Gemini, implements the A* meal planner, and manages Firebase Firestore. This role is the signing authority for technical deliverables related to the API and database.

- Flutter Developer: Develops the mobile application, including all UI screens, camera integration, and local storage. This role ensures that the frontend correctly consumes the backend APIs.

- QA / Tester: Creates test plans, executes unit/integration tests, tracks defects, and produces the UAT Report (Deliverable D13). The QA role has the authority to block a release if critical (P1) bugs remain unresolved.

- UI/UX Designer: Designs wireframes, high-fidelity mockups, and the overall user experience. Although not a signing authority, the designer’s work must be approved by the PM and the nutrition expert for usability and clarity.

- DevOps Engineer (part-time): Sets up the CI/CD pipeline, monitors cloud deployment, and manages environment variables. This role ensures that production releases are stable and repeatable.

## 9.2 Responsibilities of Stakeholders for Various Aspects of the Project

The following table summarises which stakeholder is responsible for key project aspects. Paragraphs follow the table.

| PROJECT ASPECT | RESPONSIBLE STAKEHOLDER(S) | NATURE OF RESPONSIBILITY |
| --- | --- | --- |
| Requirements definition | PM, Nutrition Expert, Beta Testers | Provide input, validate user stories |
| Technical architecture | ML Engineer, Backend Developer, DevOps | Design and document system components |
| UI/UX design | UI/UX Designer, PM | Create and approve mockups |
| Model training & evaluation | ML Engineer, PM | Achieve accuracy targets, report results |
| API development | Backend Developer | Deliver endpoints, performance, documentation |
| Frontend development | Flutter Developer, QA | Implement screens, integrate APIs, test |
| Quality assurance | QA, PM | Execute test plans, sign off on releases |
| Budget and schedule | PM | Track costs, adjust timeline, report to management |
| Risk management | PM, Expert consultant | Identify risks, implement mitigations |
| Stakeholder communication | PM | Regular updates, steering committee meetings |
| Post‑launch monitoring | DevOps, PM | Ensure uptime, collect analytics |

Beyond the table, it is important to note that the Nutrition Expert is specifically responsible for reviewing the meal database (200:300 meals) to confirm that the calorie, protein, carbohydrate, and fat values are accurate for typical portion sizes. This expert also validates the TDEE formula used during onboarding. Without this sign-off, the meal planner’s recommendations could be nutritionally misleading, which would harm user trust and project credibility.

The Project Manager holds ultimate responsibility for integrating all stakeholder contributions and ensuring that the final product meets the success criteria defined in Section 4.2. The PM also manages the external dependency on Google Gemini API by monitoring usage and maintaining a fallback plan.

## 9.3 Deliverables Stakeholders Are Responsible For & Signing Authorities

Each major deliverable requires formal sign-off by a specific stakeholder before the project can move to the next phase. This ensures accountability and quality control.

| DELIVERABLE | RESPONSIBLE STAKEHOLDER (CREATOR) | SIGNING AUTHORITY (APPROVER) | HOW SIGN‑OFF IS OBTAINED |
| --- | --- | --- | --- |
| Trained MobileNetV2 Model (D1) | ML Engineer | PM + Expert (nutrition/AI) | Model evaluation report emailed; approval recorded in meeting minutes |
| Flask API (D2) | Backend Developer | PM + QA | API passes all integration tests; QA signs test report |
| Flutter Mobile App (D4) | Flutter Developer | PM + QA | App passes UAT; no P1 bugs; QA issues sign‑off certificate |
| Onboarding Flow (D9) | Flutter Developer + UI/UX Designer | PM + Beta Testers (representative) | 5 beta testers complete onboarding without errors; PM confirms |
| UAT Report (D13) | QA | PM + Nutrition Expert | Report reviewed; all critical feedback addressed; expert signs |
| Deployment Package (D14) | DevOps + Flutter Developer | PM + (if external) Google Play Console | App published to internal track; PM verifies live URL |
| Technical & User Documentation (D15) | Backend Developer + Flutter Developer | PM | Documentation reviewed for completeness; PM signs |

### 9.4. Signing Authorities Defined:

- Project Manager (PM) is the primary signing authority for all deliverables. No deliverable is considered complete without the PM’s written approval (email or signed document).

- Nutrition Expert has signing authority over any deliverable that affects nutritional accuracy, including the meal database, TDEE calculation, and the A* planner’s recommendation logic. This expert’s signature is mandatory before the UAT phase can begin.

- QA has the authority to reject a release if critical (P1) bugs are unresolved. The QA’s sign-off on the UAT Report is a prerequisite for deployment.

- Beta Testers do not have formal sign-off authority, but their collective feedback (e.g., 80% satisfaction rating) is treated as a binding condition for launch. The PM ensures that beta tester concerns are addressed before final approval.

Process for Obtaining Sign-off:
For each deliverable, the responsible stakeholder submits a completion notification to the PM via email or project management tool (e.g., Jira, Trello). The PM then arranges a review meeting with the relevant signing authority. If approved, the signing authority adds their name and date to a central “Sign-off Log” maintained in the project’s shared drive. If rejected, the deliverable is returned with specific change requests and a new review date is scheduled.

# 10. EXPERT

## 10.1. Expert Chosen, His Domain, Job Title

| FIELD | DETAILS |
| --- | --- |
| NAME | Mohammad Kashif |
| DOMAIN | Machine Learning (ML), Deep Learning (DL), Image Processing, Computer Vision, Biometrics, & Practical Electronics. |
| JOB TITLE | Lecturer at FAST National University of Computer and Emerging Sciences (FAST-NUCES), Karachi Campus (2024:Present); Lab Instructor at PAF-KIET (2023-2024). |
| EDUCATION | BE (Electronics) from PAF-KIET MS (Computer Science) from Bahria University |

## 10.2. Why Have You Chosen Him As An Expert?

Mr. Mohammad Kashif is uniquely qualified for this project due to the direct alignment of his expertise with the core technical challenges of NutriLens. The following reasons justify his selection:

- Deep Technical Alignment: The NutriLens project is fundamentally an AI-powered computer vision application that relies on image classification (food recognition). Mr. Kashif's domain expertise in Image Processing, Computer Vision, Deep Learning (CNN/MobileNetV2), and Biometrics is precisely the skill set required to guide the team on model selection, training, evaluation, and optimization.

- Practical Experience: His professional experience as a Python Developer is invaluable as the entire backend API and ML model training pipeline is being built in Python (Flask, TensorFlow). Furthermore, his experience in Industrial ERP (4 years) provides him with a practical understanding of system design and data flows in a business context, which is useful for the integration of the Flask API and Firebase database.

- Academic Credibility: As a current Lecturer at FAST-NUCES, he is a trusted academic authority. The project team is from FAST-NUCES, so consulting an internal expert ensures easy accessibility for regular meetings. His role ensures that the project meets the academic and technical rigor expected of a final year project.

- Objectivity & Critical Review: His background in teaching and research allows him to provide unbiased, critical feedback on the technical deliverables, ensuring that the model architecture, data preparation, and evaluation metrics are scientifically sound and not just "built to work."

## 10.3. His Past Experiences & Success

- Industrial Experience (4 Years in ERP): Mr. Kashif has worked on enterprise resource planning systems. This experience is crucial for helping the team structure the meal database and backend logic in a robust, scalable manner, avoiding common pitfalls in data modeling and API design that a purely academic team might make.

- Teaching Experience (3 Years): He has successfully taught and guided multiple student projects in Computer Vision and Deep Learning. His ability to identify common mistakes (e.g., data leakage, overfitting, poor dataset preparation) will help the team proactively avoid these issues during the development of the MobileNetV2 model.

## 10.4. His Role in the Project

Mr. Kashif's role in the NutriLens project is that of an External Technical Advisor and Consultant. His specific responsibilities are:

- Validation of WBS: He is responsible for reviewing and signing off the Work Breakdown Structure (WBS) to ensure it contains a realistic number of activities (≥180) and accurately reflects the technical steps required for AI/ML development.

- Technical Verification: He will review the technical architecture, data pre-processing pipeline, and model evaluation strategy to ensure they are sound and will help achieve the goal of ≥75% Top-1 accuracy.

- Risk Assessment: He will assist in identifying technical risks related to the ML lifecycle (e.g., data availability, model overfitting, hardware constraints) and suggest mitigation strategies.

- Milestone Review: He will be consulted at the end of Phase 3 (ML Development) to review the trained model's performance and provide feedback before integration with the backend begins.

# 11. WORK BREAKDOWN STRUCTURE

Legend:  ■ Dark Blue = Phase (Level 1)   ■ Mid Blue = Sub-Phase (Level 2)   ■ White/Grey = Activity (Level 3)

| WBS No. | Task / Activity Name | Notes / Deliverable |
| --- | --- | --- |
| 1.0 | INITIATION & PLANNING PHASE |  |
| 1.1 | Project Charter & Business Case Finalization | Signed Charter |
| 1.1.1 | Review NutriLens problem statement and AI-driven opportunity |  |
| 1.1.2 | Define initial project scope (snap-to-log, macro tracking, meal planner) |  |
| 1.1.3 | Identify primary stakeholders (PM, ML Eng, Backend, Flutter Dev, QA, UI/UX, DevOps) |  |
| 1.1.4 | Secure initial management approval for planning phase |  |
| 1.1.5 | Establish project environment (Jira, GitHub, Google Drive, Slack) |  |
| 1.2 | Requirements Gathering & Analysis | Signed Requirement Spec |
| 1.2.1 | Plan requirement collection sessions with team and nutrition consultant |  |
| 1.2.2 | Document functional requirements (food classification, macro calc, meal planner) |  |
| 1.2.3 | Document non-functional requirements (latency <2s, accuracy ≥75%, privacy) |  |
| 1.2.4 | Conduct user surveys to validate pain points (manual logging, local cuisine gap) |  |
| 1.2.5 | Document South-Asian cuisine gap and plan top-3 confidence score workaround |  |
| 1.2.6 | Prioritize MVP features vs. post-MVP (custom dataset, iOS, barcode scan) |  |
| 1.2.7 | Review and baseline final Requirement Specification Document with stakeholders |  |
| 1.3 | Feasibility Analysis Finalization | Feasibility Report |
| 1.3.1 | Finalize Technical Feasibility (MobileNetV2, TFLite, Flutter, Firebase, Flask) |  |
| 1.3.2 | Finalize Operational Feasibility (snap-to-log UX, user retention strategy) |  |
| 1.3.3 | Finalize Economic Feasibility (Firebase free tier, Gemini pay-as-you-go, ROI) |  |
| 1.3.4 | Finalize Schedule Feasibility (7:8 month timeline confirmation) |  |
| 1.3.5 | Document Critical Success Factors (accuracy, latency, retention, Play Store) |  |
| 1.4 | Technology Stack & Architecture Selection | Architecture Decision |
| 1.4.1 | Confirm tech stack: Flutter, Flask, Firebase, MobileNetV2, Gemini Flash 2.0 |  |
| 1.4.2 | Define system architecture (client ↔ Flask API ↔ Firebase ↔ Gemini/TFLite) |  |
| 1.4.3 | Select Agile Scrum process model (2-week sprints, 7-8 month timeline) |  |
| 1.4.4 | Conduct architecture review meeting with ML and backend experts |  |
| 1.5 | Project Plan Finalization | Signed Project Plan |
| 1.5.1 | Finalize Work Breakdown Structure (WBS) with numbering system |  |
| 1.5.2 | Finalize time estimates and Scrum sprint schedule (Sprints 1:14) |  |
| 1.5.3 | Finalize resource sheet, team roles, and time-phased budget |  |
| 1.5.4 | Finalize Risk Register (5 identified risks with mitigation plans) |  |
| 1.5.5 | Get Project Plan signed off by PM and expert consultant |  |
| 2.0 | DESIGN PHASE |  |
| 2.1 | System Architecture & API Design | Architecture Doc |
| 2.1.1 | Design system context diagram (Flutter App ↔ Flask ↔ Firebase ↔ Gemini) |  |
| 2.1.2 | Design high-level component diagram (ML module, API, DB, UI layers) |  |
| 2.1.3 | Design Flask REST API endpoint structure (classification, planner, auth) |  |
| 2.1.4 | Define Gemini Flash 2.0 integration approach (portion estimation, fallback) |  |
| 2.1.5 | Define security architecture (Firebase Auth, API key management) |  |
| 2.2 | Database & Data Model Design | ERD + Firestore Schema |
| 2.2.1 | Design Firebase Firestore collection schema (users, meal_logs, meals, streaks) |  |
| 2.2.2 | Design meal database schema (200:300 meals with macros and dietary tags) |  |
| 2.2.3 | Define TDEE and macro calculation logic (Mifflin-St Jeor formula) |  |
| 2.2.4 | Define Firestore indexing and security rules |  |
| 2.2.5 | Review database design with nutrition expert consultant |  |
| 2.3 | UI/UX Design | High-Fidelity Mockups |
| 2.3.1 | Design wireframes for Onboarding Flow (5-step setup: stats, goal, diet pref) |  |
| 2.3.2 | Design wireframes for Camera & Snap-to-Log screen |  |
| 2.3.3 | Design wireframes for Macro Dashboard (progress bars, daily goals) |  |
| 2.3.4 | Design wireframes for AI Meal Planner screen |  |
| 2.3.5 | Design wireframes for Meal Log History (paginated, thumbnails) |  |
| 2.3.6 | Design wireframes for Weekly Streak Tracker UI |  |
| 2.3.7 | Design wireframes for Profile Management screen |  |
| 2.3.8 | Create high-fidelity mockups and define style guide (colors, typography) |  |
| 2.3.9 | Conduct usability review with pilot users and revise designs |  |
| 2.4 | ML Model Architecture Design | Model Design Spec |
| 2.4.1 | Confirm MobileNetV2 transfer learning approach on Food-101 dataset (101 classes) |  |
| 2.4.2 | Define model input/output spec (image → top-3 classes + confidence scores) |  |
| 2.4.3 | Plan TensorFlow Lite conversion and quantization strategy for on-device inference |  |
| 2.4.4 | Define model evaluation criteria (≥75% Top-1, ≥90% Top-5 accuracy) |  |
| 2.4.5 | Design finalized, reviewed and approved (Design Freeze) |  |
| 3.0 | ML DEVELOPMENT PHASE |  |
| 3.1 | Data Preparation | Prepared Dataset |
| 3.1.1 | Download and extract Food-101 dataset (101,000 images, 101 categories) |  |
| 3.1.2 | Perform data cleaning and remove corrupted/mislabeled samples |  |
| 3.1.3 | Apply data augmentation (rotation, flip, brightness, zoom) |  |
| 3.1.4 | Split dataset into train/validation/test sets (70/15/15) |  |
| 3.1.5 | Normalize and preprocess images for MobileNetV2 input requirements |  |
| 3.2 | Model Training & Fine-Tuning | Trained Model |
| 3.2.1 | Load pre-trained MobileNetV2 (ImageNet weights) and configure top layers |  |
| 3.2.2 | Train classification head (freeze base layers, 10 epochs) |  |
| 3.2.3 | Fine-tune top MobileNetV2 layers (unfreeze, lower learning rate) |  |
| 3.2.4 | Evaluate model on validation set: log accuracy, precision, recall |  |
| 3.2.5 | Tune hyperparameters (learning rate, dropout, batch size) to hit ≥75% Top-1 |  |
| 3.2.6 | Evaluate final model on held-out test set and document results |  |
| 3.3 | Model Export & Integration | TFLite Model (.tflite) |
| 3.3.1 | Convert trained Keras model to TensorFlow Lite (.tflite) |  |
| 3.3.2 | Apply post-training quantization (int8) to reduce model size to <50 MB |  |
| 3.3.3 | Validate TFLite model accuracy matches original Keras model |  |
| 3.3.4 | Test on-device inference time on 3 Android device tiers |  |
| 3.3.5 | Package TFLite model + label map for Flutter integration |  |
| 4.0 | BACKEND DEVELOPMENT PHASE |  |
| 4.1 | Environment Setup & Core API | Deployed Dev Backend |
| 4.1.1 | Setup Python virtual environment, install Flask, dependencies |  |
| 4.1.2 | Configure Firebase Admin SDK and Firestore connection |  |
| 4.1.3 | Implement JWT-based authentication middleware (Firebase Auth) |  |
| 4.1.4 | Create base API structure with error handling and logging |  |
| 4.1.5 | Setup GitHub repository, branching strategy, and CI/CD pipeline |  |
| 4.2 | Food Classification API | Classification Endpoint |
| 4.2.1 | Develop /classify endpoint (accept image → run TFLite → return top-3) |  |
| 4.2.2 | Integrate TFLite model serving in Flask (or cloud-based fallback) |  |
| 4.2.3 | Implement confidence score filtering and response formatting |  |
| 4.2.4 | Write unit tests for classification endpoint (mock images, expected labels) |  |
| 4.3 | Gemini Integration (Portion Estimation) | Portion Estimation Endpoint |
| 4.3.1 | Integrate Google Gemini Flash 2.0 API for portion size estimation |  |
| 4.3.2 | Develop /estimate-portion endpoint (image + food label → portion + adjusted macros) |  |
| 4.3.3 | Implement graceful fallback to average portion if Gemini API fails (<3s timeout) |  |
| 4.3.4 | Validate portion estimation output with nutrition expert consultant |  |
| 4.4 | A* Meal Planner Module | Meal Planner Endpoint |
| 4.4.1 | Populate Firestore meal database (200:300 meals with macros, dietary tags) |  |
| 4.4.2 | Implement A* search algorithm (current macros + target → recommended meals) |  |
| 4.4.3 | Develop /meal-plan endpoint returning 3 suggestions within 1 second |  |
| 4.4.4 | Implement dietary filter logic (Vegetarian / Non-Veg / Both) |  |
| 4.4.5 | Test meal planner with edge cases (near-goal state, empty log) |  |
| 4.5 | User & Macro Management APIs | User Data Endpoints |
| 4.5.1 | Develop /onboarding endpoint (store name, gender, age, weight, height, goal) |  |
| 4.5.2 | Implement Mifflin-St Jeor TDEE calculation and macro target setting |  |
| 4.5.3 | Develop /log-meal endpoint (store meal log entry to Firestore) |  |
| 4.5.4 | Develop /macro-summary endpoint (return daily totals vs. targets) |  |
| 4.5.5 | Develop /streak endpoint (calculate and update consecutive logging streak) |  |
| 4.5.6 | Develop /history endpoint (paginated meal log retrieval, 20 items/page) |  |
| 4.6 | Backend Testing & Deployment | Backend on Railway/Render |
| 4.6.1 | Write integration tests for all API endpoints |  |
| 4.6.2 | Perform load testing (50 concurrent users, <500ms response) |  |
| 4.6.3 | Generate Swagger/OpenAPI documentation for all endpoints |  |
| 4.6.4 | Deploy backend to Railway/Render with environment variables configured |  |
| 4.6.5 | Configure Firebase Firestore security rules for production |  |
| 5.0 | FRONTEND (FLUTTER) DEVELOPMENT PHASE |  |
| 5.1 | Project Setup & Core Configuration | Flutter Project Initialized |
| 5.1.1 | Create Flutter project, configure Firebase (google-services.json, FirebaseOptions) |  |
| 5.1.2 | Setup state management (Provider), routing, and folder structure |  |
| 5.1.3 | Implement Firebase Auth (Email/Password + Google Sign-In) |  |
| 5.1.4 | Configure camera plugin and image picker for meal photo capture |  |
| 5.1.5 | Define global theme (colors, typography, reusable widgets) |  |
| 5.2 | Onboarding Flow (5 Steps) | Deliverable D9 |
| 5.2.1 | Build Step 1 : Name & Gender input screen with validation |  |
| 5.2.2 | Build Step 2 : Age & Weight input screen (age: 13-100, weight > 0) |  |
| 5.2.3 | Build Step 3 : Height input screen |  |
| 5.2.4 | Build Step 4 : Fitness Goal selection (weight loss, muscle gain, maintain) |  |
| 5.2.5 | Build Step 5 : Dietary Preference selection (Vegetarian / Non-Veg / Both) |  |
| 5.2.6 | Implement onboarding completion and data save to Firestore via API |  |
| 5.3 | Camera & Snap-to-Log Screen | Core MVP Feature |
| 5.3.1 | Build camera capture screen with real-time preview |  |
| 5.3.2 | Integrate /classify API call on image capture |  |
| 5.3.3 | Display top-3 classification results with confidence scores |  |
| 5.3.4 | Implement food selection confirmation and manual override option |  |
| 5.3.5 | Trigger /estimate-portion call after food selection |  |
| 5.3.6 | Display estimated macros and confirm log to Firestore |  |
| 5.4 | Macro Dashboard | Deliverable D10 |
| 5.4.1 | Build real-time macro dashboard with progress bars (calories, protein, carbs, fat) |  |
| 5.4.2 | Implement live update after each meal log (call /macro-summary) |  |
| 5.4.3 | Display daily goal vs. consumed with percentage indicators |  |
| 5.4.4 | Add quick-access button to camera capture and meal planner |  |
| 5.5 | AI Meal Planner Screen | Deliverable D6 |
| 5.5.1 | Build meal planner UI displaying 3 recommended meals from /meal-plan |  |
| 5.5.2 | Implement dietary filter toggle (Vegetarian / Non-Veg / Both) |  |
| 5.5.3 | Show macro breakdown for each recommended meal card |  |
| 5.5.4 | Implement log recommended meal directly from planner screen |  |
| 5.6 | Meal Log History Screen | Deliverable D11 |
| 5.6.1 | Build paginated meal log history (20 items/page, reverse chronological) |  |
| 5.6.2 | Display thumbnail, food name, macros, and timestamp per log entry |  |
| 5.6.3 | Implement pull-to-refresh and scroll-based lazy loading |  |
| 5.7 | Weekly Streak Tracker | Deliverable D8 |
| 5.7.1 | Build 7-day streak view (highlighted days, streak count) |  |
| 5.7.2 | Implement streak increment logic (at least 1 meal/calendar day) |  |
| 5.7.3 | Implement streak reset after missed day and push reminder notification |  |
| 5.8 | Profile Management Screen | User Profile Feature |
| 5.8.1 | Build profile screen displaying user stats (age, weight, goal) |  |
| 5.8.2 | Implement edit functionality (update stats, re-calculate TDEE) |  |
| 5.8.3 | Add logout button with Firebase Auth sign-out |  |
| 5.9 | Cross-Cutting Concerns | App Polish |
| 5.9.1 | Implement input validation and graceful error handling throughout app |  |
| 5.9.2 | Ensure responsiveness across screen sizes (5" to 6.5" Android devices) |  |
| 5.9.3 | Implement loading indicators and optimistic UI updates |  |
| 5.9.4 | Code review, cleanup, and merge all feature branches |  |
| 6.0 | TESTING & QUALITY ASSURANCE PHASE |  |
| 6.1 | Unit Testing | Unit Test Sign-off |
| 6.1.1 | Write unit tests for TDEE/macro calculation logic |  |
| 6.1.2 | Write unit tests for A* meal planner algorithm |  |
| 6.1.3 | Write unit tests for streak logic (increment, reset, edge cases) |  |
| 6.1.4 | Execute unit tests and log results |  |
| 6.1.5 | Fix defects found during unit testing and re-test |  |
| 6.2 | Integration Testing | Integration Test Sign-off |
| 6.2.1 | Test snap-to-log flow (camera → classify → portion estimate → log) |  |
| 6.2.2 | Test meal planner refresh after each meal log |  |
| 6.2.3 | Test onboarding → TDEE calculation → dashboard initial display |  |
| 6.2.4 | Fix and re-test all integration defects |  |
| 6.3 | System & Performance Testing | Performance Report |
| 6.3.1 | Measure end-to-end latency (photo to macro log) on 5 Android devices |  |
| 6.3.2 | Perform API load testing (50 concurrent users, validate <500ms response) |  |
| 6.3.3 | Test TFLite model classification accuracy on 500-sample test batch |  |
| 6.3.4 | Test Gemini fallback behavior when API times out |  |
| 6.3.5 | Conduct security review (Firebase rules, API key exposure check) |  |
| 6.3.6 | Document performance benchmarks and obtain QA sign-off |  |
| 6.4 | User Acceptance Testing (UAT) | Deliverable D13: UAT Report |
| 6.4.1 | Recruit 20 beta users for 7-day UAT session |  |
| 6.4.2 | Distribute beta APK and prepare test scenarios / feedback form |  |
| 6.4.3 | Monitor usage, collect bug reports and satisfaction ratings (target ≥4.0/5.0) |  |
| 6.4.4 | Fix all P1 (crash/data loss) bugs identified during UAT |  |
| 6.4.5 | Obtain UAT final sign-off from PM and beta users |  |
| 7.0 | DEPLOYMENT PHASE |  |
| 7.1 | Infrastructure & Production Setup | Production Environment Ready |
| 7.1.1 | Configure production environment on Railway/Render (env vars, SSL) |  |
| 7.1.2 | Configure Firebase Firestore production security rules and backups |  |
| 7.1.3 | Setup monitoring and alerting (uptime, API error rate, latency) |  |
| 7.1.4 | Perform smoke test on production backend |  |
| 7.2 | Google Play Store Deployment | Deliverable D14 |
| 7.2.1 | Build release APK/AAB with production Firebase config |  |
| 7.2.2 | Prepare Play Store listing (screenshots, description, privacy policy) |  |
| 7.2.3 | Submit app to Google Play internal testing track |  |
| 7.2.4 | Address any Play Store policy review feedback |  |
| 7.2.5 | Promote app to production and announce Go-Live |  |
| 7.3 | Documentation | Deliverable D15 |
| 7.3.1 | Finalize Swagger/OpenAPI documentation for all Flask endpoints |  |
| 7.3.2 | Write user manual with screenshots and FAQs |  |
| 7.3.3 | Write maintenance guide (model update process, Firestore backup, env setup) |  |
| 7.3.4 | Conduct documentation review with PM and obtain sign-off |  |
| 8.0 | PROJECT CLOSURE PHASE |  |
| 8.1 | Post-Launch Monitoring & Stabilization | Stability Report |
| 8.1.1 | Monitor app performance and Gemini API costs for 2 weeks post-launch |  |
| 8.1.2 | Collect user feedback via in-app survey (meal planner rating target ≥4.0/5.0) |  |
| 8.1.3 | Implement critical hotfixes if production issues arise |  |
| 8.1.4 | Track Firebase Analytics: onboarding completion rate (≥85%) and DAU |  |
| 8.2 | Project Review & Lessons Learned | PIR Report |
| 8.2.1 | Conduct post-implementation review (PIR) against SMART goals |  |
| 8.2.2 | Document lessons learned (ML training time, Gemini API integration) |  |
| 8.2.3 | Archive project artifacts (code, docs, WBS, risk register) to Google Drive |  |
| 8.2.4 | Obtain final project sign-off from all stakeholders |  |
| 8.2.5 | Handover to maintenance team and officially close project |  |

# 12. RISK MANAGEMENT

## 12.1. IDENTIFIED PROJECT RISKS AND MITIGATION STRATEGIES

The following five high-priority risks have been identified for the NutriLens project in consultation with the project expert. Each risk is described with its probability, impact, severity rating, and a concrete mitigation strategy.

| # | RISK | CATEGORY | PROBABILITY | IMPACT | SEVERITY | MITIGATION STRATEGY |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Low ML Model Accuracy | Technical | High | High | Critical | Display top-3 predictions with confidence scores and allow manual override. Apply data augmentation and fine-tune MobileNetV2 top layers. Set accuracy checkpoint ≥75% Top-1 at Sprint 3; retrain if not met. |
| 2 | Google Gemini API Downtime or Cost Spike | Technical / Financial | Medium | High | High | Implement fallback to average portion size estimation (small/medium/large with user confirmation). Monitor API costs weekly; set billing alerts. Budget $50/month for API; upgrade plan if needed. |
| 3 | Backend Cold Start Delays (Free Tier Hosting) | Technical | High | Medium | High | Implement keep-alive ping every 10 minutes to prevent cold starts. Set latency threshold at 2 seconds. Upgrade to Railway/Render paid tier ($5:20/month) if cold starts persist during beta testing. |
| 4 | Key Resource Unavailability (ML Engineer) | Resource | Medium | High | High | Document all training scripts, configurations, and model checkpoints from Sprint 1. Cross-train Backend Developer on basic model evaluation. Maintain a 1-week schedule buffer for ML phase. |
| 5 | Google Play Store Rejection | Regulatory / Legal | Medium | High | High | Register Play Store developer account in Phase 1. Prepare privacy policy with legal review. Submit to internal testing track 3 weeks before planned launch. Follow Google Play policy checklist from the start. |

## 12.2. RISK SEVERITY JUSTIFICATION

All five risks above are rated Critical or High severity because NutriLens is an AI-driven product where technical failures directly impact user experience and project viability.

- LOW MODEL ACCURACY (RISK 1) makes the core feature unusable. If the app cannot correctly identify food, users will abandon it immediately, rendering the entire project ineffective.

- API DEPENDENCY (RISK 2) AND HOSTING INSTABILITY (RISK 3) affect system reliability. The portion estimation feature and backend availability are essential for a seamless user experience; any disruption here leads to user frustration and negative reviews.

- RESOURCE UNAVAILABILITY (RISK 4) can halt the most time-consuming phase of the project. The ML Engineer is the only team member with specialized deep learning expertise, and their absence would delay the entire AI pipeline.

- PLAY STORE REJECTION (RISK 5) can delay the final deliverable entirely. Without distribution through Google Play, the app cannot reach users, making the project incomplete from a delivery standpoint.

Each mitigation strategy has been reviewed and approved by the project expert to ensure practical feasibility within the 7:8 month timeline and available budget constraints.